## ABD Project 1 Estimate (Pilot)
Sample Pilot Program Estimate
[5 empty] | External Organization Labor Estimate | External Organization Resources | External Organization Cost Estimate | Our Company Labor Estimate | Our Company Resources | Total Labor Estimate
Reuse Management |  |  |  |  | 150
Initialize Pilot Project
|  | Setup the Reuse program |  |  | 121
Activities
|  |  | 1. Initiate Reuse Program |  | 16 | LabSvcsRep | 4800
|  |  | 2. Conduct Reuse Assessment |  | 16 | LabSvcsRep | 4800
|  |  | 3. Define Reuse Strategy |  | 40 | LabSvcsRep, TechRep1, TechRep2 | 10666.6667
|  |  | 4. Establish Reuse Infrastructure |  | 40 | LabSvcsRep, TechRep1, TechRep2 | 10666.6667
|  |  | 5. Scope Pilot Project |  | 8 | LabSvcsRep, TechRep1, TechRep2 | 2133.3333
|  |  | 6. Provide Financial Support |  | 1 | LabSvcsRep | 300
Artifacts & Deliverables
Reuse adoption and incentive plan
Reuse assessment
Reuse strategy
Pilot Project, and future projects, resources plan & estimates
Reuse guidelines
a. Asset naming, documentation and classification standards
b. Asset development and application development workflows
d. Component architecture modeling guidance
|  | Prepare for Monitor Reuse Program |  |  | 29
Activities
|  |  | 1. Identify Reuse Opportunity |  | 8 | TechRep1, TechRep2 | 2000
|  |  | 2. Prepare for Measure Reuse Activity |  | 6 | LabSvcsRep, TechRep1, TechRep2 | 1600
|  |  | 3. Prepare for Report Reuse Activity |  | 9 | LabSvcsRep, TechRep1, TechRep2 | 2400
|  |  | 4. Prepare for Refine Reuse Program Activity |  | 6 | LabSvcsRep, TechRep1, TechRep2 | 1600
Artifacts & Deliverables
Candidate asset selection criteria
Initial candidate assets identified
Initial reuse metric definitions
Reuse status report format and promotional material
Asset Management |  |  |  |  | 84
Prepare Environment
|  | Establish Reuse Environment |  |  | 52
Activities
|  |  | 1. Define Asset Workflows |  | 24 | LabSvcsRep, TechRep1, TechRep2 | 6400
|  |  | 2. Setup the Asset production environment |  | 8 | LabSvcsRep, TechRep1, TechRep2 | 2133.3333
|  |  | 3. Setup the Asset consumption environment |  | 8 | LabSvcsRep, TechRep1, TechRep2 | 2133.3333
|  |  | 4. Setup the Asset management environment |  | 12 | LabSvcsRep, TechRep1, TechRep2 | 3200
Artifacts & Deliverables
Producer asset development workflow
Consumer asset development workflow
Asset-based application development workflow
Asset review and certification workflow
CQ schema
Training material for Asset Producers, Consumers, Librarians, Maintainers
Reuse guidelines
Reusable asset survey
Asset/Artifacts versioning policy & guidelines
|  | Prepare for Provide Assets |  |  | 16
Activities
|  |  | 1. Prepare for Package Asset activity |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
|  |  | 2. Prepare for Review Asset activity |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
|  |  | 3. Prepare for Publish Asset activity |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
|  |  | 4. Prepare for Modify Asset activity |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
Artifacts & Deliverables
Reusable asset organization document
Change request document
Asset feedback document
Asset review and certification workflow
|  | Prepare for Retire Assets |  |  | 2
Activities
|  |  | 1. Prepare for Retire Asset activity |  | 2 | TechRep1, TechRep2 | 500
Artifacts & Deliverables
Retire asset steps
|  | Prepare for Manage Assets |  |  | 7
Activities
|  |  | 1. Prepare for Track Asset Metrics activity |  | 1 | TechRep1, TechRep2 | 250
|  |  | 2. Create Asset Survey |  | 4 | TechRep1, TechRep2 | 1000
|  |  | 3. Prepare for Refine Reuse Environment activity |  | 2 | TechRep1, TechRep2 | 500
Artifacts & Deliverables
Reusable asset survey
|  | Prepare for Produce Assets |  |  | 2
Activities
|  |  | 1. Prepare for Develop Asset activity |  | 1 | TechRep1, TechRep2 | 250
|  |  | 2. Prepare for Harvest Asset activity |  | 1 | TechRep1, TechRep2 | 250
|  | Prepare for Consume Assets |  |  | 5
Activities
|  |  | 1. Prepare for Locate Asset activity |  | 1 | TechRep1, TechRep2 | 250
|  |  | 2. Prepare for Apply Asset activity |  | 2 | TechRep1, TechRep2 | 500
|  |  | 3. Prepare for Rate Asset activity |  | 2 | TechRep1, TechRep2 | 500
Asset Production & Consumption |  |  |  |  | 280
Execute Asset-based Development Workflows
|  | Execute Producer Asset Development Workflow |  |  | 121
Activities
|  |  | 1. Harvest Assets |  | 40 | LabSvcsRep, TechRep1, TechRep2 | 10666.6667
|  |  | 2. Package Assets |  | 60 | LabSvcsRep, TechRep1, TechRep2 | 16000
|  |  | 3. Review Assets |  | 18 | LabSvcsRep, TechRep1, TechRep2 | 4800
|  |  | 4. Publish Assets |  | 3 | LabSvcsRep, TechRep1, TechRep2 | 800
Artifacts & Deliverables
Use Case / Architecture View asset(s)
Deployment asset(s)
Component Design model asset(s)
Other assets
Asset test and review results
|  | Execute Consumer Asset Development Workflow |  |  | 90
Activities
|  |  | 1. Apply Producer Assets |  | 8 | LabSvcsRep, TechRep1, TechRep2 | 2133.3333
|  |  | 3. Create Component Architecture Specification |  | 32 | LabSvcsRep, TechRep1, TechRep2 | 8533.3333
|  |  | 4. Create IDE Projects |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
|  |  | 5. Harvest assets |  | 8 | LabSvcsRep, TechRep1, TechRep2 | 2133.3333
|  |  | 6. Package assets |  | 32 | LabSvcsRep, TechRep1, TechRep2 | 8533.3333
|  |  | 7. Review assets |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
|  |  | 8. Publish assets |  | 2 | LabSvcsRep, TechRep1, TechRep2 | 533.3333
Artifacts & Deliverables
Use Case / Architecture View / Deployment asset(s)
Component Design model asset(s)
Asset test and review results
|  | Execute Asset-based Application Development Workflow |  |  | 6
Activities
|  |  | 1. Locate asset |  | 1 | LabSvcsRep, TechRep1, TechRep2 | 266.6667
|  |  | 2. Apply asset |  | 4 | LabSvcsRep, TechRep1, TechRep2 | 1066.6667
|  |  | 3. Rate asset |  | 1 | LabSvcsRep, TechRep1, TechRep2 | 266.6667
Artifacts & Deliverables
Asset feedback
Change request
|  | Execute Producer Asset Development Workflow (update producer assets) |  |  | 39
Activities
|  |  | 1. Modify Asset |  | 16 | TechRep1, TechRep2 | 4000
|  |  | 2. Package Asset |  | 16 | TechRep1, TechRep2 | 4000
|  |  | 3. Review Asset |  | 4 | TechRep1, TechRep2 | 1000
|  |  | 4. Publish Asset |  | 1 | TechRep1, TechRep2 | 250
|  |  | 5. Retire Asset |  | 2 | TechRep1, TechRep2 | 500
Artifacts & Deliverables
Use Case / Architecture View asset(s)
Deployment asset(s)
Component Design model asset(s)
Other assets
Asset test and review results
|  | Execute Consumer Asset Development Workflow (update consumer assets) |  |  | 20
Activities
|  |  | 1. Apply Producer assets |  | 4 | TechRep1, TechRep2 | 1000
|  |  | 3. Create Component Architcture Specification |  | 4 | TechRep1, TechRep2 | 1000
|  |  | 4. Create IDE projects |  | 2 | TechRep1, TechRep2 | 500
|  |  | 5. Modify asset |  | 4 | TechRep1, TechRep2 | 1000
|  |  | 6. Package assets |  | 2 | TechRep1, TechRep2 | 500
|  |  | 7. Review assets |  | 2 | TechRep1, TechRep2 | 500
|  |  | 8. Publish assets |  | 2 | TechRep1, TechRep2 | 500
Artifacts & Deliverables
Use Case / Architecture View / Deployment asset(s)
Component Design model asset(s)
Asset test and review results
|  | Execute Asset-based Application Development Workflow (apply updated assets) |  |  | 4
Activities
|  |  | 1. Locate asset |  | 1 | TechRep1, TechRep2 | 250
|  |  | 2. Apply asset |  | 2 | TechRep1, TechRep2 | 500
|  |  | 3. Rate asset |  | 1 | TechRep1, TechRep2 | 250
Artifacts & Deliverables
Asset feedback
Change request
Reuse Management |  |  |  |  | 30
Review and Refine
|  | Monitor Reuse Program |  |  | 30
Activities
|  |  | 1. Identify Reuse Opportunity |  | 6 | LabSvcsRep, TechRep1, TechRep2 | 1600
|  |  | 2. Measure Reuse |  | 6 | LabSvcsRep, TechRep1, TechRep2 | 1600
|  |  | 3. Report Reuse |  | 9 | LabSvcsRep, TechRep1, TechRep2 | 2400
|  |  | 4. Refine Reuse Program |  | 9 | LabSvcsRep, TechRep1, TechRep2 | 2400
Artifacts & Deliverables
Reuse adoption and incentive plan
Reuse assessment
Reuse strategy
Pilot project, and future projects, resources plan & estimates
Reuse guidelines
Asset nameing, documentation and classification standards
Asset development and application development workflows
IBM e-business patterns guidance
Component architecture modeling guidance
IDE project creation guidance
Summary
|  | Total Hours |  |  | 544 |  | 144716.6667
|  | Total Person Days |  |  | 68
|  | Total People |  |  | 3
|  | Total Timeline Days |  |  | 22.6667
Rates
LabSvcsRep
300
TechRep1
250
TechRep2
250
Note on D25: Facilitate reuse education Identify reuse heritage Identify candidate reuse activities Estimate organization readiness Address asset governance issues Identify business motivation Identify sponsor
Note on D26: Determine reuse potential and aptitude Examine business goals and objectives Determine economic feasibility Identify reuse adoption goals
Note on D27: Define reuse vision Create vision strategy and identify risks Evaluate organization and process impact Identify metrics for measuring progress Refine the reuse adoption and incentive plan Investigate tool infrastructure Create reuse guidelines
Note on D28: Identify tooling Acquire and setup tooling Train personnel Refine reuse guidelines
Note on D29: Determine pilot project scope, objectives, and success criteria -- Determine Asset Producer assets for pilot -- Determine Asset Consumer assets for pilot
Note on D30: Review reuse strategy, guidelines, and resources plan Evaluate current reuse program results Determine funding model for the reuse program Prepare pilot project and future project estimates
Note on D43: Create candidate asset selection criteria Apply candidate asset selection criteria Create candidate asset descriptions
Note on D44: Define Asset Consumer metrics Define Asset Management metrics Define Asset Production metrics Define business driver metrics
Note on D45: Prepare promotion and status material Promote reuse program and communicate status
Note on D46: Prepare policy for reviewing and refining the reuse program Determine reuse program stakeholders
Note on D58: Refine the Producer Asset Development workflow Refine Consumer Asset Development workflow Refine the Asset Review and Certification workflow Refine Asset-based Application Development workflow
Note on D59: Establish the tooling and refine reuse guidelines to support -- Develop Asset -- Harvest Asset -- Test Asset -- Package Asset -- Review Asset Refine the Producer Asset Development workflow Refine the Consumer Asset Development workflow Prepare the Asset Producer repository organization Train Asset Producers and Asset Reviewers
Note on D60: Establish the tooling and refine reuse guidelines to support -- Locate Asset -- Apply Asset -- Rate Asset Refine the Asset-based Application Development workflow Prepare the Asset Consumer repository organization Train Asset Consumers
Note on D61: Determine asset & artifact versioning policies Establish the tooling and refine reuse guidelines to support -- Publish Asset -- Track Asset Metrics -- Create Asset Survey -- Modify Asset Refine the Asset Review and Certification workflow Train Asset Librarians and Asset Maintainers
Note on D76: Determine the Asset Consumer’s user experience Refine the asset artifacts, documents and installation organization Test the asset in the Asset Consumer’s environment (functional correctness and user experience)
Note on D77: Refine the Asset Review and Certification workflow Test the Asset Review and Certification workflow
Note on D78: Identify the location where the Asset Librarian can receive the asset Determine further categorization of the asset before publishing Prepare supporting artifacts such as asset support information and asset feedback Determine how assets will be made available/visible to Asset Consumers
Note on D79: Create the asset’s Change Request documents Prepare asset / artifact modification environment Verify the asset validation / testing environment
Note on D89: Determine the repositories and supporting artifacts to be updated Determine views and reports to be updated
Note on D96: Determine how to track and capture asset metrics
Note on D97: Identify the recurring problems Asset Consumers face Determine solutions available with current assets Determine problem coverage with the solutions Create an asset survey
Note on D98: Determine policy for refining reuse environment Evaluate existing asset feedback Update the reuse environment
Note on D105: Review candidate asset selection criteria Verify test environment is established Verify asset organization and documentation
Note on D106: Review candidate asset selection criteria Refine artifact harvesting policy Verify test environment is established Verify asset organization and documentation
Note on D110: Verify directed search and non-directed search for assets in Asset Producer and Asset Consumer repositories Verify asset documentation to assess applicability of assets
Note on D111: Verify asset retrieval and installation from Asset Producer and Asset Consumer repositories Refine asset re-packaging strategy for Asset Producers
Note on D112: Verify asset feedback mechanism
Note on D118: Define the Candidate Assets Discover / Create artifacts Prepare artifacts for reuse Test harvested artifacts Create usage instructions
Note on D119: Determine the target user-experience Refine the asset organization Develop installation support materials Complete the asset documentation Test asset in the Asset Consumer's environment (functional correctness, user experience)
Note on D120: Execute the Asset Review and Certification workflow Record and communicate the results
Note on D121: Submit assets to Asset Producer Repository
Note on D132: Review Reference model Review Project requirements Initialize IDE project(s) Reuse template assets [use case and architecture view asset(s)]
Note on D133: Produce models for component architecture specification Reuse Asset Producer assets [component design model(s)]
Note on D134: Create projects for specified components Reuse Asset Producer assets [other assets, security, exception handling, …]
Note on D135: Customize models and assets for Asset Consumers Discover / Create additional artifacts, as necessary Prepare artifacts for reuse Test harvested artifacts Create usage instructions
Note on D136: Package and certify assets Determine the target user-experience Refine the asset organization Develop installation support materials Complete the asset documentation Test asset in the Asset Consumer’s environment (verify semantics/functional correctness/ user experience)
Note on D137: Execute the Asset Review and Certification workflow Record and communicate the results
Note on D138: Submit assets to Asset Consumer Repository
Note on D147: Search for Use Case and Component Design Assets Browse Assets Assess Applicability of Assets Accept Assets
Note on D148: Acquire Asset Configure Asset
Note on D149: Provide feedback Create change request
Note on D157: Understand the asset’s Change Requests and Asset Feedback [use case and architecture view asset(s), deployment asset(s), component design model asset(s)] Acquire approval for modifications Modify artifacts, documentation, installation Validate the asset Update asset’s version
Note on D158: Determine the target user-experience Refine the asset organization Develop installation support materials Complete the asset documentation Test asset in the Asset Consumer’s environment (verify semantics/functional correctness/ user experience)
Note on D159: Execute the Asset Review and Certification workflow Record and communicate the results
Note on D160: Submit asset to Asset Consumer repository
Note on D161: Update the Reusable Asset Library Update views and reports
Note on D172: Review Reference model Review Project requirements Initialize IDE project(s) Reuse Asset Producer assets [use case and architecture view asset(s)]
Note on D173: Produce models for component architecture specification Reuse Asset Producer assets [component design model(s)]
Note on D174: Create projects for specified components Reuse template assets [other assets, security, exception handling, …]
Note on D175: Understand the asset’s Change Requests and Asset Feedback [use case and architecture view asset(s), deployment asset(s), component design model asset(s)] Acquire approval for modifications Modify artifacts, documentation, installation Validate the asset Update asset’s version
Note on D176: Package and certify assets Determine the target user-experience Refine the asset organization Develop installation support materials Complete the asset documentation Test asset in the Asset Consumer’s environment (verify semantics/functional correctness/ user experience)
Note on D177: Execute the Asset Review and Certification workflow Record and communicate the results
Note on D178: Submit assets to Asset Consumer Repository
Note on D187: Search for Use Case and Component Design Assets Browse Assets Assess Applicability of Assets Accept Assets
Note on D188: Acquire Asset Configure Asset
Note on D189: Provide feedback Create change request
Note on D199: Apply candidate asset selection criteria Create candidate asset description
Note on D200: Collect asset consumer metrics Collect asset management metrics Collect asset production metrics Collect business driver metrics
Note on D201: Prepare promotion and status material Promote reuse program and communicate status
Note on D202: Evaluate policies, feedback and status Determine modifications Gain stakeholder approval Implement changes